## Milestone Schedule
Milestone # | Milestone | Exit Citeria /Deliverable | Due Date | Payment | Funded | CLIN SUBCLIN | ACRN
1 | Kickoff Meeting: A briefing on the technical plan for the effort to include milestone schedule and path to accomplish the objectives of the agreement. Report on documented, modeling- and simulation-supported experimental plans for reaching performer-specified fluence and power density objectives prior to month 15 | Milestone report describing design approach to meeting the metrics and goals for base period | Month 2
2 | Report on real time unit cell test on unit cell Rev 1.0 with constantly emitting radiation source to acquire fluence and degradation data | Milestone report summarizing performance of materials and architectures to withstand radiation per base period metrics | Month 8
3 | Report on real time unit cell test on unit cell Rev 2.0 with constantly emitting radiation source to acquire fluence and degradation data | Milestone report summarizing performance of materials and architectures to withstand radiation per base period metrics | Month 11
4 | Report documenting the verification of unit cell’s ability to withstand >1E+14/cm2 fluence at approximately 0% degradation | Milestone report summarizing performance of materials and architectures to withstand radiation per base period metrics. Report will synthesize data from all experiments in order to support metrics and competitive down-select. | Month 14
5 | Report on proposed operational system power and mass estimate to calculate specific power for reaching the >10 W/kg metric | Milestone report summarizing performance of materials and architectures to withstand radiation per base period metrics. Report will synthesize data from all experiments in order to support metrics and competitive down-select. This report will include modleing and simulation results to capture operational system parameters. | Month 14
Sub-Total Base Period |  |  |  | 0 | 0
6 | Report on modeling and simulation to support experimental plans validating performer-specified fluence and power density objectives prior to month 24 | Milestone report describing design approach to meeting the metrics and goals for base period | Month 16 |  | 0 | TBD | TBD
7 | Report on real-time test on unit cell Rev N.0 with constantly emitting radiation source to acquire fluence and degradation data | Milestone report summarizing performance of materials and architectures to withstand radiation per base period metrics | Month 18 |  | 0 | TBD | TBD
8 | Report on real-time test on unit cell Rev N.N with constantly emitting radiation source to acquire fluence and degradation data | Milestone report summarizing performance of materials and architectures to withstand radiation per base period metrics | Month 20 |  | 0 | TBD | TBD
9 | Report on the ability of unit cell to withstand >1E+17/cm2 fluence at <20% degradation | Milestone report summarizing performance of materials and architectures to withstand radiation per base period metrics. Report will synthesize data from all experiments in order to support metrics and competitive down-select. | Month 23 |  | 0 | TBD | TBD
10 | Performer report on IV&V team’s post-irradiation examination of the unit cell used in linac test, and the unit cell used in time capsule test, with a comparison of the degradation of each cell | Milestone report summarizing performance of materials and architectures to withstand radiation per base period metrics. Report will synthesize data from all experiments in order to support metrics and competitive down-select. | Month 23 |  | 0 | TBD | TBD
Sub-Total Option Period 1 |  |  |  | 0 | 0
11 | Final report transmitted with results of scalability study for transition partner | Final report which utilizes data obtained throughout course of program as evidence to support the scalability study's operational system performance. This final report will include an updated and refined specific power estimate. This report will include a conceptual design, such as CAD rendering with primary structural elements, to include the radiovoltaic developed in the course of the program, which will make it possible to fabricate the full scale system at the end of the option period 2. | Month 30 |  | 0 | TBD | TBD
Sub-Total Option Period 2 (Bonus) |  |  |  | 0
Total Agreement |  |  |  | 0 | 0
*Tasks and targets are keyed to Attachment 1 - Task Description Document
HIGHLIGHTED SECTION NOT TO BE FILLED OUT BY PROPOSERS